## Sheet1
| 12 months |  |  |  | 11 months |  |  |  | 10 months |  |  |  | 9 months |  |  |  | 8 months |  |  |  | 7 months |  |  |  | 6 months |  |  |  | 5 months |  |  |  | 4 months |  |  |  | 3 months |  |  |  | 2 months |  |  |  | 1 month |  |  |  | Month of
Number of Weeks Until TTW | T- 51 | T- 50 | T- 49 | T- 48 | T- 47 | T- 46 | T- 45 | T- 44 | T- 43 | T- 42 | T- 41 | T- 40 | T- 39 | T- 38 | T- 37 | T- 36 | T- 35 | T- 34 | T- 33 | T- 32 | T- 31 | T- 30 | T- 29 | T- 28 | T- 27 | T- 26 | T- 25 | T- 24 | T- 23 | T- 22 | T- 21 | T- 20 | T- 19 | T- 18 | T- 17 | T- 16 | T-15 | T- 14 | T- 13 | T- 12 | T- 11 | T- 10 | T- 9 | T- 8 | T- 7 | T- 6 | T- 5 | T- 4 | T- 3 | T- 2 | T- 1 | Week Of | Week After
Tribute to Women Tasks
Select date
Book the venue
Establish color and theme
Selection Committee
Determine possible committee members
Send invitations to possible members
Send confirmations to members
Schedule Selection meeting
Selection meeting
Awardees
Call for nominations
Reminder for nominations
Congratulatory letter
Regrets nomination letter
Bios/Quotes
Headshots
Photo releases
Engraved awards
Invite lists
Nomination submission deadline
Summary of nomination to committee
Sponsorship
Determine sponsorship levels
Premier request
Confirm Premier
Honorary Chair request
Honorary Chair confirmation
Sponosorship requests for renewal
New sponsorship requests
Reservation forms (deadline and sent out)
Request ad's
Table lists
Design Print Mail
Request design/header from Alphagraphics
STD to Alphagraphics
STD mailed
STD reminder to Alphagraphics
STD reminder
Invitations to Alphagraphics
Mail inviations
Mail completementary invitations
Order signs from Alphagraphics
Program book content to Alphagraphics
Letter from Governor
Letter from County Executive
Collect ad's from sponsors
Edit Bio's/Quotes
Program book to Kreider for printing
Table Design
Sponsorship table layout
Dias seating
Board assignments (working the room)
Individual table assignments
Table Tents
Menu
Donation Envelopes
Favors
Media
Calendar listing in local papers
Nomination announcements
Business Times listing
Local media coverage request
Press release
Raffle
Item request
Buy baskets/package items
Organize tickets/envelopes
Request cash for change
Script/timeline
Write and review
Send to speakers
Volunteers
Send out request for volunteers
Volunteer meeting
Volunteer assignments
Finance
Create budget master
Ticket sales
Sponsorship payments
Online Updates
Social Media Updates
Website updates
Other
Emcee
Interpreter
Reverend for invocation
PowerPoint
Start Thank You video
Thank you's/acknowledgments
Recap/evaluation